## Sheet1
FORM NO. B210-2 |  |  | INVOICE CONTINUATION SHEET FOR CAPITAL CONSTRUCTION
PROJECT NAME: |  | Enter Project Name as Shown on Award Letter | [8 empty] | Sheet | 1
PROJECT LOCATION: |  | Nearest City or Specific Location Information | [8 empty] | of | 1
ITEM | DESCRIPTION OF WORK | AMOUNT | BREAKDOWN |  | COMPLETED TO DATE |  | MATERIALS STORED ON SITE | AMOUNT COMPLETED THIS MONTH | TOTAL COMPLETED TO DATE | % COMPLETED | PREVIOUSLY BILLED | BALANCE REMAINING
|  |  | LABOR | MATERIALS | LABOR | MATERIALS
1 | JOB MOBILIZATION | 53000 | 5000 | 48000 | [7 empty] | 0
2 | EXC. FILLING AND GRADING | 110000 | 110000 | [8 empty] | 0
3 | PAVING | 8000 | 3000 | 5000 | [7 empty] | 0
4 | SITE WORK CONCRETE | 47000 | 25000 | 22000 | [7 empty] | 0
5 | BRICK PAVING | 18000 | 12000 | 6000 | [7 empty] | 0
6 | SODDING | 10000 | 4000 | 6000 | [7 empty] | 0
7 | BUILDING CONCRETE | 590000 | 325000 | 265000 | [7 empty] | 0
8 | PRECAST CONCRETE | 139000 | 23000 | 116000 | [7 empty] | 0
9 | MASONRY | 192000 | 120000 | 72000 | [7 empty] | 0
10 | MISC & ORN METAL | 65000 | 15000 | 50000 | [7 empty] | 0
11 | CARPENTRY & MILLWORK | 11000 | 3000 | 8000 | [7 empty] | 0
12 | WATERPROOFING | 2700 | 1700 | 1000 | [7 empty] | 0
13 | ROOFING AND RELATED WORK | 20000 | 8000 | 12000 | [7 empty] | 0
14 | CAULKING | 12000 | 7000 | 5000 | [7 empty] | 0
15 | SKYLIGHT | 4000 | 1000 | 3000 | [7 empty] | 0
16 | GLASS, GLAZING, ALUMN | 17000 | 7000 | 10000 | [7 empty] | 0
17 | ALUMINUM WINDOWS | 59000 | 10000 | 49000 | [7 empty] | 0
18 | HOLLOW METAL | 29000 | 9000 | 20000 | [7 empty] | 0
19 | WOOD DOORS | 24000 | 6000 | 18000 | [7 empty] | 0
20 | HARDWARE | 37000 | 7000 | 30000 | [7 empty] | 0
21 | LATHING AND PLASTERING | 25000 | 13000 | 12000 | [7 empty] | 0
22 | ACOUSTICAL CEILINGS | 29000 | 9000 | 20000 | [7 empty] | 0
23 | RESILIENT TILE | 31000 | 8000 | 23000
24 | CERAMIC TILE | 67000 | 35000 | 32000
25 | PAINTING | 40000 | 32000 | 8000
26 | MISC EQUIPMENT | 32000 | 2000 | 30000
27 | BUILT IN FURNITURE | 138000 | 16000 | 122000
28 | VENETIAN BLINDS | 5000 | 1000 | 4000
29 | CARPET | 3000 | 1000 | 2000
30 | ELEVATORS | 122000 | 42000 | 80000
31 | MECHANICAL | 0
32 | PLUMBING - EXTERIOR WORK | 50000 | 46000 | 4000
33 | PLUMBING FIXTURES | 38000 | 16000 | 22000
34 | PLUMBING PIPING AND MISC | 153000 | 68000 | 85000
35 | HVAC EQUIPMENT | 92000 | 22000 | 70000
36 | VENT PIPING VALVES FITTINGS | 134000 | 78000 | 56000
37 | HEATING - SHEET METAL | 24000 | 20000 | 4000
38 | HEATING CONTROLS | 32000 | 12000 | 20000
39 | PLUMBING HEATING INSUL | 32000 | 22000 | 10000
40 | ELECTRICAL | 0
41 | CONDUIT AND WIRE | 90000 | 50000 | 40000
42 | SERVICE EQUIPMENT | 37000 | 5000 | 32000
43 | SPECIAL SYSTEMS | 20000 | 2000 | 18000
44 | FIXTURES | 49000 | 7000 | 42000
45 | FINISH WIRING DEVICES | 6000 | 3000 | 3000
46 | GEN & LIGHTING PROTECTION | 9000 | 1000 | 8000
| Totals | 2705700 | 1212700 | 1493000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Do not include materials stored on site in this column.
"Total completed to date" may include materials stored on site.
EXAMPLE